## Sheet2
Project Name: | XXXXXX
Project Duration (months): | 3-12 months
Activity | Responsibility | June 2020 | July 2020 | August 2020
START UP PHASE
Set up company emails and acquire business cards | Flavian Machimbirike | a
Set up meeting with Reserve Bank of Zimbabwe, National Payments System (NPS) | Flavian Machimbirike Diana Chakarisa | a
Identify and schedule meetings with potential sponsor banks | Diana Chakarisa | a
Request for all Corporate Governance documentation from xxxxxxxxxx | xxxxxxx |  | a
Complie all documents and information required by NPS | Flavian Machimbirike Diana Chakarisa |  | a
Move ahead to Implementation phase |  |  | a